## Sheet1
Activity | Complete By Date | Time Line | Patrol / Adult Advisor | Tour Coordinator | Status | Note/Comment
Activity:
Pre- Plannning
Align on Trip program purpose |  | 29SF-24 wks
Outline Program activities |  | 29SF-24 wks
Investigate location/ alternatives |  | 29SF-24 wks
Develop plan
Select program concept |  | 29SF-16 wks
align on site selection |  | 29SF-16 wks
make site reservation |  | 29SF-12 wks
align on back-up plan |  | 29SF-9 wks
Establish transportation plan |  | 29SF-9 wks
File Tour permit |  | 29SF-8 wks
Establish activity fee |  | 29SF-8 wks
create activity sheet |  | 29SF-8 wks
Begin detailed planning
Publish Web article |  | 29SF-6 wks
File Tour permit |  | 29SF-6 wks
send out marketing email |  | 29SF-6 wks
SPL to announce at troop meetings |  | 29SF-4 wks
re-confirm site reservation |  | 29SF-4 wks
Finalize plan
finalize the program plan |  | 29SF-2 wks
print extra forms for fron desk |  | 29SF-2 wks
Final Roster |  | 29SF-2 wks
Finalize the trip roster with the registrar |  | 29SF-2 wks |  |  |  |  | Align on Trip program purpose
Establish list of transportation drives |  | 29SF-2 wks |  |  |  |  | Investigate location/ alternatives
Assemble Health forms with Resigistrar |  | 29SF-2 wks |  |  |  |  | Select program concept
Prepare event forms with Tour leader |  | 29SF-2 wks |  |  |  |  | align on site selection
Execute trip date: